## Staffing Plan (hidden)
Customer
MSX-ID
Date |  | FY Uplift (%)
Price to Win |  | Week to start FY uplift
No Price to Win | - | Sold Margin | 21.63% |  | Delivery Capacity (hrs)
Revenue | 6506840 | Margin Variance (26.7%) | -5.075% | Infrastructure | 4856
Cost | 5056635.5945 | Governance (% of hours) | 13.8% | AI | 6024
|  | Partner Allocation (% of hours) | 0% | Development | 5280
Risk Reserve | $0 at 0% | Total Hours | 25594 | Security | 240
T&E | 0 | Suggested BE Range | Low: $6507000 - High: $7809000 | ASCM | 0
Other Items |  | Additional Calculators
Travel and Expenses |  | Governance Calculator: Please run and include a screenshot of the results. |  | DM Governance Calculator - Power Apps
Risk Reserve (%) |  | Delivery Compliance, Privacy and Security (DCPS) Estimator: |  | Compliance Security Estimator
[17 empty] | Pre-Init | Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5
|  | Role | Role Title | Role to Resource Mapping | Role to Functional Area Mapping | Resource Type | Resource Notes and Proposed Individual | Total Hours | List Rate | Bill Rate | Cost Rate | Revenue | Delivery Cost | Sold Margin % | Discount (Premium)% | Total Allocation % | WK0 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45
|  | Governance Team | 13.8% | [8 empty] | - | - | bar: Pre-Init WK0 to Sprint 5 WK28
|  | DME | Delivery Management Executive | Delivery Management Executive1 |  |  |  | 94 | 460 | 460 | 458.1842 | 43240 | 43069.3119 | 0.3947% | 0% | 0.6645% |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Program Architect | Program Architect | Program Architect1 | AI |  |  | 808 | 500 | 500 | 461.1845 | 404000 | 372637.049 | 7.763% | 0% | 6.209% | 8 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Program Manager | Senior Project Manager | Senior Project Manager1 |  |  |  | 960 | 370 | 370 | 258.3668 | 355200 | 248032.1182 | 30.17% | 0% | 5.459% |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
|  | Scrum Master / Project Manager | GD Offshore | GD Offshore1 |  |  |  | 960 | 90 | 90 | 53.8867 | 86400 | 51731.2025 | 40.13% | 0% | 1.328% |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
|  | TQA | GD Offshore | GD Offshore2 |  |  |  | 100 | 90 | 90 | 53.8867 | 9000 | 5388.6669 | 40.13% | 0% | 0.1383% |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
|  |  | 0% | [8 empty] | - | - | bar: Pre-Init WK0 to Sprint 5 WK28
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
|  | AI Landing Zone / Infra | 25.53% | [8 empty] | - | - | bar: Pre-Init WK0 to Sprint 5 WK28
|  | App/ Infra Architect | Senior Domain Solution Architect | Senior Domain Solution Architect1 | AI |  | Azure Infra/Landing Zone | 1208 | 490 | 490 | 404.1545 | 591920 | 488218.66 | 17.52% | 0% | 9.097% | 8 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
|  | Sr. Consultant (Infra) | Senior Consultant | Senior Consultant1 | Infrastructure |  | Azure Infra/Landing Zone | 1608 | 365 | 365 | 256.1502 | 586920 | 411889.5401 | 29.82% | 0% | 9.02% | 8 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | App/ Infra Consultant | GD Offshore | GD Offshore1 | Infrastructure |  | Azure Infra/Landing Zone | 1600 | 90 | 90 | 53.8867 | 144000 | 86218.6708 | 40.13% | 0% | 2.213% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | DevOps Consultant | GD Offshore | GD Offshore2 | Infrastructure |  | Intune | 1560 | 90 | 90 | 53.8867 | 140400 | 84063.204 | 40.13% | 0% | 2.158% |  | 20 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | DevOps Consultant | GD Offshore | GD Offshore3 | Infrastructure |  | Intune | 1560 | 90 | 90 | 53.8867 | 140400 | 84063.204 | 40.13% | 0% | 2.158% |  | 20 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Security Consultant | GD Offshore | Senior Consultant2 | Infrastructure |  | Intune | 640 | 90 | 90 | 53.8867 | 57600 | 34487.4683 | 40.13% | 0% | 0.8852% |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
|  |  |  | Senior Domain Soultion Architect2 | Security |  | Intune | 0 | - | - | - | - | - | - | 0% | 0%
|  | In Vehicle (Edge) - Agentic Solution -AI SLM, Model Tuning | 40.68% | [8 empty] | - | - | bar: Pre-Init WK0 to Sprint 5 WK28
|  | Prin Data Scientist | Principal Data Scientist | Principal Data Scientist1 | AI |  | Language Model training and fine tunning | 808 | 500 | 500 | 367.3109 | 404000 | 296787.1864 | 26.54% | 0% | 6.209% | 8 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Sr. Data Scientist | Data Scientist | Data Scientist1 | AI |  | Speech To Text Model training and fine tunning | 808 | 400 | 400 | 360.6281 | 323200 | 291387.5006 | 9.843% | 0% | 4.967% | 8 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Sr. Data Scientist | Data Scientist | Data Scientist2 | AI |  | Speech To Speech Model training and fine tunning | 1600 | 400 | 400 | 360.6281 | 640000 | 577004.9517 | 9.843% | 0% | 9.836% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Sr. Data Scientist | Data Scientist | Data Scientist3 | AI |  | Text to Speech Model training and fine tuning | 1600 | 400 | 400 | 360.6281 | 640000 | 577004.9517 | 9.843% | 0% | 9.836% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Sr. Data Scientist | Data Scientist | Data Scientist4 | AI |  | Wakeup word/VAD training and fine tuning | 1600 | 400 | 400 | 360.6281 | 640000 | 577004.9517 | 9.843% | 0% | 9.836% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Sr. Consultant | Senior Consultant | Senior Consultant1 | Development |  | Car Integration, Dev Lead | 800 | 365 | 365 | 256.1502 | 292000 | 204920.1692 | 29.82% | 0% | 4.488% |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Sr. Consultant | Senior Consultant | Senior Consultant2 | Development |  | DevOps/MLOps, CI/CD | 800 | 365 | 365 | 256.1502 | 292000 | 204920.1692 | 29.82% | 0% | 4.488% |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Consultant / Developer | GD Offshore | GD Offshore4 | Development |  | Developer | 1600 | 90 | 90 | 53.8867 | 144000 | 86218.6708 | 40.13% | 0% | 2.213% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Consultant / Developer | GD Offshore | GD Offshore5 | Development |  | Developer | 1600 | 90 | 90 | 53.8867 | 144000 | 86218.6708 | 40.13% | 0% | 2.213% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Tester | GD Offshore | GD Offshore6 | Development |  | Tester | 1440 | 90 | 90 | 53.8867 | 129600 | 77596.8037 | 40.13% | 0% | 1.992% | [5 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Tester | GD Offshore | GD Offshore7 | Development |  | Tester | 1440 | 90 | 90 | 53.8867 | 129600 | 77596.8037 | 40.13% | 0% | 1.992% | [5 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | RAI | Security Architect |  | AI |  | RAI Review | 160 | 445 | 445 | 404.1545 | 71200 | 64664.7232 | 9.179% | 0% | 1.094% |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
|  | [Other Workstreams….] | 0% | [8 empty] | - | - | bar: Pre-Init WK0 to Sprint 5 WK28
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
|  |  | 0% | [8 empty] | - | - | bar: Pre-Init WK0 to Sprint 5 WK28
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
|  | Secure By Default | 1.509% | [8 empty] | - | - | bar: Pre-Init WK0 to Sprint 5 WK28
|  | Architect | Security Architect |  | Security |  | SBD | 48 | 445 | 445 | 404.1545 | 21360 | 19399.417 | 9.179% | 0% | 0.3283% | Sprint 0 WK1: 4; Sprint 0 WK2: 4; Sprint 1 WK3: 4; Sprint 1 WK4: 4; Sprint 2 WK5: 4; Sprint 2 WK6: 4; Sprint 3 WK7: 4; Sprint 3 WK8: 4; Sprint 4 WK9: 4; Sprint 4 WK10: 4; Sprint 5 WK11: 4; Sprint 5 WK12: 4
|  | Sr. Consultant | Security Consultant |  | Security |  | SBD | 192 | 400 | 400 | 256.1502 | 76800 | 49180.8406 | 35.96% | 0% | 1.18% | Sprint 0 WK1: 16; Sprint 0 WK2: 16; Sprint 1 WK3: 16; Sprint 1 WK4: 16; Sprint 2 WK5: 16; Sprint 2 WK6: 16; Sprint 3 WK7: 16; Sprint 3 WK8: 16; Sprint 4 WK9: 16; Sprint 4 WK10: 16; Sprint 5 WK11: 16; Sprint 5 WK12: 16
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
[8 empty] | 0 | - | - | - | - | - | - | 0% | 0%
Note on C4: Jeffrey Rosen: default is 3% leave cell blank/empty unless you intend for uplift. If week to start FY uplift is blank, the % will apply for all weeks.
Note on C5: Jeffrey Rosen: Just use a number, e.g. 10 to start the uplift applying in week 10 to the end. Leave cell blank to not apply uplift.
Note on F6: Jeffrey Rosen: If cell is Red, this indicates insufficient capacity vs estimated capacity
Note on B14: Typical estimate is 2k per person per week * # trips
Note on B15: 7% Std, 14% High
Note on E18: WHO: Architect Description: Purpose of this column is to map roles to physical resources. For example, you may have the Project Manager and Scrum master with the same role title, use this field to map them to indicate they are the same individual.
Note on G18: WHO: Architect Description: Indicates when we need to identify partner resources to generate a partner allocation caculation.
Note on H18: WHO: Architect Description: The purpose of this column is to provide general notes outside the GRM skills, however, leverage the "Resource Skills" worksheet to indicate the specific GRM skills required for the individual.
Note on K18: WHO: Pursuit Lead Description: The amount we charge the client per hour of work. Defaults to List Rate, but if there is a discount, apply the discounted bill rate here and override the default assignment to the List Rate.

## Assumptions (hidden)
Assumptions for Cloud Hub Infra Estimates
1. Landing Zone (CAF Enterprise-Scale)
Management group hierarchy (Bosch Platform → Landing Zones → per-OEM subscriptions)
Subscription vending automation and the shared Cloud Hub platform sub
Azure Policy initiatives: CAF baseline + Bosch-custom + per-OEM regulatory; mandatory tagging enforced
Azure Blueprints / Bicep or Terraform module that provisions the entire stack below per subscription
2. Networking & Connectivity
Hub-spoke topology: hub vNet, Azure Firewall, Azure Bastion
Per spoke vNet (/22) with subnet plan for APIM, AI Foundry private endpoints, AI Search, Cosmos DB, Event Hub, MCP Server compute, Key Vault
Private Endpoints for every PaaS service (AI Foundry, AI Search, Cosmos, Event Hub, Key Vault, Monitor)
Azure Front Door
3. API Management Gateway (APIM) — Provisioned
Azure API Management (Premium, internal/VNet-injected) deployed per OEM subscription
Backend pool placeholders for: AI Foundry model endpoints, MCP Servers, Cloud Agents, Other Agents
Policies provisioned as templates only: rate limit, JWT validation against Entra, request logging to Event Hub, Application Insights diagnostics
LLM access pattern wired: all model calls (Azure OpenAI / Foundry models) routed through APIM
Developer portal published; product/subscription model defined; no live operations imported
4. Agent Orchestration & Hosting Platform — Infra Only
Azure AI Foundry hub + project provisioned per OEM (private networking, customer-managed keys via Key Vault)
Compute substrate for agent hosting provisioned (AKS cluster or Azure Container Apps environment + Azure Functions Premium plan — chosen during Sprint 0): node pools, managed identities, ingress controller, namespace-per-agent-class
Service Bus / Event Grid topics provisioned for inter agent messaging contracts
Container registry (ACR Premium with geo-replication, content trust, Defender scanning) provisioned and empty
5. MCP Server Hosting Infrastructure — Provisioned
Dedicated Container Apps environment (or AKS namespace) for Cloud MCP Servers with mTLS-ready ingress
Outbound connectivity through Azure Firewall to Bosch backend systems (allow-listed FQDNs)
Managed identity per planned MCP server with RBAC scoped to Key Vault secrets references
APIM facade pattern provisioned (route → MCP server backend pool)
6. AI Search & Data Plane — Provisioned
Azure AI Search (Standard S2+, private endpoint, semantic ranker SKU) — no indexes, no skillsets, no data sources created
Azure Cosmos DB (User Context Store) — account, database, and container shells with partition key strategy; no data, no documents
Azure Event Hub namespace + hubs for telemetry and ingestion — capture to ADLS configured, no producers wired
7. LLM Access Pattern
Azure OpenAI / Foundry model deployments provisioned (GPT-4o / o-series / embedding model — exact SKUs per Sprint 0 sizing)
Model endpoints exposed only through APIM ; APIM products map OEM → allowed model deployments
Content Safety resource provisioned with default policies
8. Observability
Azure Monitor + Log Analytics workspace(s) per OEM with retention/archival policy
Application Insights resources provisioned per planned agent / MCP service (
Diagnostic settings forced on every resource above via Azure Policy (DeployIfNotExists)
Baseline Workbooks: APIM throughput/latency, Foundry model token usage, AKS/ACA health, Key Vault access — dashboards live, agent-level dashboards stubbed
9. DevOps / Platform Engineering
Single IaC repo (Bicep or Terraform — locked Sprint 0) with module library covering every component above
GitHub Actions or ADO pipelines: env promotion (dev → test → preprod → prod), policy-as-code gates, security scans (PSRule / tfsec / Checkov), drift detection
GitOps-ready: AKS/ACA bootstrapped with Flux or ArgoCD configuration (no workloads synced)
ACR Assumptions —
A. Vehicle Profile Mix
Profile | Mix %
Premium | 20%
Mid-Tier | 50%
Basic | 30%
Total | 100%
B. Per-Vehicle Interaction Model
Driver | Premium | Mid-Tier | Basic | Unit | Notes
Active days per year | 330 | 330 | 330 | days | Days vehicle is in active use
Interactions per day | 50 | 35 | 30 | count | Total user-AI exchanges per active day
Cloud offload rate | 10% | 35% | 80% | % | Fraction handled by Azure (vs. edge SLM)
Cost per cloud chain | 0.025 | 0.018 | 0.012 | $ | Avg orchestrator+agent+RAG chain cost (Azure OpenAI)
Telemetry per day | 50 | 15 | 5 | MB | Edge-filtered upload to Event Hub
C. Other Per-Vehicle Annual Costs (USD)
Service Category | Premium | Mid-Tier | Basic | Unit | Notes
Compute & Orchestration | 6 | 10 | 14 | $/yr | AKS, APIM, agent microservices, MCP servers (allocated per active vehicle)
Content Safety + Foundry | 8 | 6 | 5 | $/yr | Azure AI Search index share, Content Safety calls, Foundry tooling overhead
Data & Storage | 18 | 10 | 5 | $/yr | Event Hub ingest, Cosmos DB user context, Fabric/Data Lake retention
Security | 4 | 4 | 4 | $/yr | Entra B2C, WAF, Defender, Key Vault (largely flat per active user)
Monitoring | 3 | 4 | 5 | $/yr | Azure Monitor + App Insights
Networking & Egress | 5 | 4 | 3 | $/yr | Vehicle ↔ cloud data path
D. Stamp Scenarios
Stamp Size | Vehicles | Fixed Cost / yr ($) |  |  | Notes
Small | 50000 | 400000 |  |  | Pilot / new-region launch
Medium | 250000 | 700000 |  |  | Regional steady state
Large | 750000 | 1200000 |  |  | Major OEM/region peak
E. Bosch Vehicle Volume Forecast
Year | Total Vehicles | China | Germany | Japan | US
2027 | 30000 | 30000 | 0 | 0 | 0
2028 | 510000 | 150000 | 260000 | 100000 | 0
2029 | 875500 | 250000 | 500000 | 100000 | 25500
2030 | 1924500 | 400000 | 750000 | 400000 | 374500
2031 | 2342500 | 400000 | 750000 | 480000 | 712500
2032 | 2585000 | 360000 | 750000 | 480000 | 995000
Per-Stamp ACR Scenarios (Small / Medium / Large)
Stamp | Vehicles | Variable ACR ($/yr) | Fixed ACR ($/yr) | Total ACR ($/yr) | $/vehicle | Notes
Small | 50000 | 5587225 | 400000 | 5987225 | 119.7445 | Pilot / new region (baseline AKS, APIM, control plane)
Medium | 250000 | 27936125 | 700000 | 28636125 | 114.5445 | Regional steady state
Large | 750000 | 83808375 | 1200000 | 85008375 | 113.3445 | Major OEM / region peak — best $/vehicle efficiency
ACR by Service Category × Stamp Size (Variable Only)
Service Category | Per-Vehicle Wtd Avg ($) | Small | Medium | Large | % of ACR
Compute & Orchestration | 10.4 | 520000 | 2600000 | 7800000 | 0.093069
AI/ML Inference (LLM+RAG+Safety+Foundry) | 79.2445 | 3962225 | 19811125 | 59433375 | 0.70916
Data & Storage | 10.1 | 505000 | 2525000 | 7575000 | 0.090385
Security | 4 | 200000 | 1000000 | 3000000 | 0.035796
Monitoring | 4.1 | 205000 | 1025000 | 3075000 | 0.036691
Networking & Egress | 3.9 | 195000 | 975000 | 2925000 | 0.034901
TOTAL Variable | 111.7445 | 5587225 | 27936125 | 83808375 | 1

## Resource Skills (hidden)
Assigned Role | Primary Skill | Second skill
Delivery Management Executive1
Program Architect1
Senior Project Manager1
GD Offshore1
GD Offshore2
Senior Domain Solution Architect1
Senior Consultant1
GD Offshore3
Senior Consultant2
Senior Domain Soultion Architect2
Principal Data Scientist1
Data Scientist1
Data Scientist2
Data Scientist3
Data Scientist4
GD Offshore4
GD Offshore5
GD Offshore6
GD Offshore7
Note on C3: The list is searchable - just start typing!

## Checklist (hidden)
1. Compass One
Completed 0 of 20
Completed | ID | Responsible
FALSE | 1.1 | Architect | Did you submit a consumption(ACR) plan or mark the exception?
FALSE | 1.2 | Pursuit Lead | Are all relevant C1 warnings cleared?
FALSE | 1.3 | Pursuit Lead | Are the "Contracting Customers” and “Supporting Customers” info populated?
FALSE | 1.4 | Pursuit Lead | Are the “Microsoft Contacts” populated correctly? (eg. Signatory should be DME, Relationship Manager=DME, unless PM identified, Primary Delivery=DME, unless PM identified)
FALSE | 1.5 | Pursuit Lead | Are the travel expectations in SOW and in ESWO and C1 consistent (i.e. if there is no travel, SOW should say 'all work is remote', if travel, did you include T&E in C1)
FALSE | 1.6 | Architect / Pursuit Lead | All of the risk assessments completed accurately and completely?
FALSE | 1.8 | Pursuit Lead | Prior to DRM preview provide links for all documents (to be reviewed) in C1 not as actual attachments; After approval by DRM Preview ensure final documents are posted as static documents
FALSE | 1.9 | Pursuit Lead | Add the reviewers to the C1 record (Add DME on the account if it is different from reviewers)
FALSE | 1.1 | Architect | Has ACSM been included where we are delivering solutions with significant change impacts?
FALSE | 1.11 | Architect | If ACSM has not been included, have we added this as a customer responsibility/out of scope and incrased the risk factor?
FALSE | 1.12 | Pursuit Lead | Contract Title contains customer name and project sort title (Ex: "Toyota: D365 Sales Transformation")
FALSE | 1.13 | Pursuit Lead | Prior to DRM, all dates in C1 and executable documents are aligned (ie. C1 "Planned Duration", C1 Financial Packages dates, SOW and ESWO dates)
FALSE | 1.14 | Pursuit Lead | For deals with ECIF, confirm IO code is entered in C1 and expiration date and amount is valid
FALSE | 1.15 | Architect | Is Sold margin >= 23.4% (FY25 threshold) or required approvals are posted in C1
FALSE | 1.16 | Pursuit Lead | Have you had at least one full review of the SOW?
FALSE | 1.17 | Pursuit Lead | Has the Area technial review or SRM been completed? (email approval for SRM)
FALSE | 1.18 | Pursuit Lead | Attach required OneAsk approval email to C1
FALSE | 1.19 | Pursuit Lead | For CR/Amendments using ECIF, have you posted documentation showing alignment to consumption plan. If CR/amendment does not impact consumption, is the purpose to prevent leakage?
FALSE | 1.2 | Pursuit Lead | All reviews and approvals from other groups completed (e.g. SSL, BizApps, etc.), and are they registered in C1?
FALSE | 1.21 | Pursuit Lead | For deals with ECIF, confirm there is sufficient time to burn ECIF before expiration, allowing for standard staffing timelines (ie. typically 4 weeks)
2. Solution
Completed 0 of 18
SOW / Overall Deal Shaping
Completed | ID
FALSE | 2.1 | Architect | Does the SOW capture via scope and assumptions what are the top customer Dependencies?
FALSE | 2.2 | Architect | Does the introduction explain what success look like to the customer
FALSE | 2.3 | Architect | Does delivery methodology: LED/Waterfall/other align to customer expectations?
FALSE | 2.4 | Architect | For Deliverables requiring acceptance, confirm they make sense? (e.g. in T&M, generally we dont have signed-off deliverables)
FALSE | 2.5 | Architect | Do you have a timeline showing the initial planned timeline for the Engagement with the multiple work-streams and not the generic timeline?
FALSE | 2.6 | Pursuit Lead | Have you completed RAI and InfoSec reviews, as required?
FALSE | 2.7 | Architect | Did you capture any expected use of OSS (Open Source Software)?
Staffing plan / Timeline
ID
FALSE | 2.6 | Architect | Did you add pre-initiation time (“Week 0”) for PjM & Architect leads with appropriate prep hours?
FALSE | 2.7 | Architect | Did you account for sufficient onboarding requirements and time (i.e. new ISD logo, Customer has significant onboarding requirements into their environment, highly regulated)
FALSE | 2.8 | Architect | If “scrum master” role required, did you specify hours separately from PjM in WBS and C1 and SOW?
FALSE | 2.9 | Architect | Does the staffing plan show a weekly breakdown?
FALSE | 2.10 | Architect | Has the Architect reviewed the skill definitions, and staffing plan (start date and end date, hours/day)?
FALSE | 2.11 | Architect | Has the Architect highlighted any scarce skill on the staffing plan?
FALSE | 2.12 | Pursuit Lead | Have you run the governance calculator and included the results in the WBS spreadsheet?
FALSE | 2.13 | Pursuit Lead | If you are below the minimum governance requirements, have you discussed the reasons with the Area CPMM?
FALSE | 2.14 | Architect | Did you map SOW LED roles to staffing plan and ensure that the SOW roles map to the WBS and map to C1
FALSE | 2.15 | Pursuit Lead | SbD required / not should be validated with Rick Alba and effort included
FALSE | 2.16 | Pursuit Lead | Staffing plan & C1 should be identical at all times
3. ESWO / Partner
Completed 0 of 5
Partner
Completed | ID
FALSE | 3.1 | Pursuit Lead | If a partner / subcon is required, has c1 been completed?
FALSE | 3.2 | Pursuit Lead | Are they approved and currently active?
FALSE | 3.3 | Pursuit Lead | Did the customer suggest the partner (a conflict of interest form is required)?
ESWO
ID
FALSE | 3.4 | Pursuit Lead | Did you mark 'PO Required Y/N' appropriately?
FALSE | 3.5 | Pursuit Lead | If any ECIF, specify and include required expiration language in ESWO

## Version (hidden)
Version | Date | Notes
0.9 | 4552300% | Updated Staffing Plan resourcing description based on( Sola Osunsan) | Training Video: | Staffing Plan Tutorial.mp4
0.91 | 4552700% | Updates Checklist with additional items (Becky Wynne)
0.92 | 4553000% | Added BE Range suggestion (Dean Sesko)
0.93 | 4557200% | Fixed cost calculation (John Gilbert)
0.94 | 4557900% | Fixed formatting
0.95 | 4558300% | Added link to "Compliance Privacy Security Estimator v2.4" workbook. (Sean Leavitt)
0.96 | 4559300% | Added beta for basis of estimation (Joe Newell)
0.97 | 4561400% | Added ability to choose custom %'s for WBS estimates
0.98 | 4561400% | Added responsible column to Checklist (Ravi Thoutireddy)
0.99 | 4574900% | updated SBD to DCPS, changed staffing to table - should make adding columns/rows better
1 | 4579900% | added ability to apply uplift
1.1 | 4585300% | Updated margin for FY26
1.2 | 4585900% | Updated to FY26 Rates

## WBS (hidden)
|  |  |  | 10% | 60% | 10%
Estimate Category | Description | Complexity | Dev Sprints or Build (hrs) | Baseline Planning or Envisioning | Testing | Deploy | Total | Category | Estimated Capacity Needed
|  |  | 10 | 1 | 6 | 1 | 18 | Infrastructure | 0
|  |  |  | 0 | 0 | 0 | 0 | AI | 0
|  |  |  | 0 | 0 | 0 | 0 | Development | 0
|  |  |  | 0 | 0 | 0 | 0 | Security | 0
|  |  |  | 0 | 0 | 0 | 0 | ASCM | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
Note on F2: Jeffrey Rosen: =Default is 10% Dev sprints/Build * 10%
Note on G2: Jeffrey Rosen: Default is 60% =Dev sprints/Build * 60%
Note on H2: Jeffrey Rosen: Default is 10% =Dev sprints/Build * 10%
Note on B3: Jeffrey Rosen: Current Categories are: Development AI Infrastructure Security ACSM
Note on C3: Jeffrey Rosen: Use description to capture what the item is. Examples: Development -> Custom API Development -> 2 Logic Apps Infrastructure -> Setup 1 secure landing zone AI -> Prompt engineering AI -> Develop custom model AI -> Fine tuning model Security -> Analyze existing DLP rules ACSM -> Custom persona development
Note on D3: Jeffrey Rosen: When assigning complexity, use this for guidelines: Low: OOB/low code Med: Custom/known pattern High: Fully custom Note, this setting has no affect on calculations. It is intended to capture and reflect the effort.
Note on E3: Jeffrey Rosen: Total hours

## CS Staffing Plan UPDATED
Customer |  | TOTAL | 3402610
MSX-ID
Date |  | FY Uplift (%)
Price to Win |  | Week to start FY uplift
No Price to Win | - | Sold Margin | 33.65% |  | Delivery Capacity (hrs) | Percentage
Revenue | 3242610 | Margin Variance (26.7%) | 6.95% | Infrastructure | 0 | 0
Cost | 2099055.4146 | Governance (% of hours) | 15.6% | AI | 3591 | 25.661
|  | Partner Allocation (% of hours) | 0% | Development | 10208 | 72.9455
Risk Reserve | $0 at 0% | Total Hours | 15872 | Security | 195 | 1.3935
T&E | 160000 | Suggested BE Range | Low: $3243000 - High: $3892000 | ASCM | 0
13994
Other Items |  | Additional Calculators
Travel and Expenses |  | Governance Calculator: Please run and include a screenshot of the results. |  | DM Governance Calculator - Power Apps
Risk Reserve (%) |  | Delivery Compliance, Privacy and Security (DCPS) Estimator: |  | Compliance Security Estimator
[17 empty] | 2026-06-24 | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30 | 2027-01-06 | 2027-01-13 | 2027-01-20 | 2027-01-27 | 2027-02-03 | 2027-02-10 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-10 | 2027-03-17 | 2027-03-24 | 2027-03-31
[17 empty] | Pre-Init | Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9 |  | Sprint 10 |  | Sprint 11 |  | Sprint 12
|  | Role | Role Title | Role to Resource Mapping | Role to Functional Area Mapping | Resource Type | Resource Notes and Proposed Individual | Total Hours | List Rate | Bill Rate | Cost Rate | Revenue | Delivery Cost | Sold Margin % | Discount (Premium)% | Total Allocation % | WK0 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40
|  | Governance Team | 15.6% | [13 empty] | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04
|  | DME | Delivery Management Executive | Delivery Management Executive1 |  | US |  | 110 | 478.4 | 478.4 | 476.51 | 52624 | 52416.1 | 0.3951% | 0% | 1.623% | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  | Program Architect | Program Architect | Program Architect1 | AI | US |  | 240 | 520 | 520 | 477.33 | 124800 | 114559.2 | 8.206% | 0% | 3.849% | 8 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | Project Manager | Senior Project Manager | Senior Project Manager1 |  | US |  | 720 | 384.8 | 384.8 | 267.41 | 277056 | 192535.2 | 30.51% | 0% | 8.544% | 16 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
|  | Scrum Master / Project Manager | GD Offshore | GD Offshore1 |  | GDC |  | 480 | 93.6 | 93.6 | 55.77 | 44928 | 26769.6 | 40.42% | 0% | 1.386% | 8 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
|  | TQA | GD Offshore | GD Offshore2 |  | GDC |  | 68 | 93.6 | 93.6 | 55.77 | 6364.8 | 3792.36 | 40.42% | 0% | 0.1963% |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  | In Vehicle (Edge) - Agentic Solution -AI SLM, Model Tuning | 83.45%
|  | Prin Data Scientist - Charlie Gu | Principal Data Scientist | Principal Data Scientist1 | AI | Singapore | Language Model training and fine tunning | 903 | 500 | 500 | 361.54 | 451500 | 326470.62 | 27.69% | 0% | 13.92% | 24 | 40 | 40 | 40 | 40 | 40 | 39 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
|  | Sr. Data Scientist Zachary Hou | Data Scientist | Data Scientist1 | AI | Indian | Speech To Text Model training and fine tunning | 384 | 416 | 416 | 375.05 | 159744 | 144019.2 | 9.844% | 0% | 4.926% | 2026-10-05: 32; 2026-10-12: 32; 2026-10-19: 32; 2026-10-26: 32; 2026-11-02: 32; 2026-11-09: 32; 2026-11-16: 32; 2026-11-23: 32; 2026-11-30: 32; 2026-12-07: 32; 2026-12-14: 32; 2026-12-21: 32
|  | Sr. Data Scientist Yoi Xiang | Data Scientist | Data Scientist2 | AI | ANZ | Speech To Speech Model training and fine tunning | 840 | 400 | 400 | 312.19 | 336000 | 262239.6 | 21.95% | 0% | 10.36% | 8 | 40 | 40 | 40 | 40 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 24 | 24 | 24
|  | Sr. Data Scientist Murumalla Krishnakant Achary | Data Scientist | Data Scientist3 | AI | China | Text to Speech Model training and fine tuning | 840 | 416 | 416 | 312.25 | 349440 | 262290 | 24.94% | 0% | 10.78% | 8 | 40 | 40 | 40 | 40 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 24 | 24 | 24
|  | Sr. Data Scientist | Data Scientist | Data Scientist4 | AI | US | Wakeup word/VAD training and fine tuning | 384 | 400 | 400 | 128.18 | 153600 | 49221.12 | 67.95% | 0% | 4.737% | 2026-10-05: 32; 2026-10-12: 32; 2026-10-19: 32; 2026-10-26: 32; 2026-11-02: 32; 2026-11-09: 32; 2026-11-16: 32; 2026-11-23: 32; 2026-11-30: 32; 2026-12-07: 32; 2026-12-14: 32; 2026-12-21: 32
|  | Sr. Consultant Yifeng Li | Senior Consultant | Senior Consultant2 | Development | China | Device Integration, Testing Framework | 840 | 365 | 365 | 137.7 | 306600 | 115668 | 62.27% | 0% | 9.455% |  | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 24 | 24 | 24
|  | Consultant / Developer | GD Offshore | GD Offshore4 | Development | GDC | Developer | 1040 | 93.6 | 93.6 | 55.77 | 97344 | 58000.8 | 40.42% | 0% | 3.002% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Consultant / Developer | GD Offshore | GD Offshore5 | Development | GDC | Tester | 1040 | 93.6 | 93.6 | 55.77 | 97344 | 58000.8 | 40.42% | 0% | 3.002% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Consultant / Developer | GD Offshore | GD Offshore6 | Development | GDC | Training Data | 1040 | 94.6 | 94.6 | 56.77 | 98384 | 59040.8 | 39.99% | 0% | 3.034% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Consultant / Developer | GD Offshore | GD Offshore7 | Development | GDC | Training Data | 1040 | 95.6 | 95.6 | 57.77 | 99424 | 60080.8 | 39.57% | 0% | 3.066% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Consultant / Developer | GD Offshore | GD Offshore8 | Development | GDC | Training Data | 1040 | 96.6 | 96.6 | 58.77 | 100464 | 61120.8 | 39.16% | 0% | 3.098% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Consultant / Developer | GD Offshore | GD Offshore9 | Development | GDC | Training Data | 1040 | 97.6 | 97.6 | 59.77 | 101504 | 62160.8 | 38.76% | 0% | 3.13% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Consultant / Developer | GD Offshore | GD Offshore10 | Development | GDC | Training Data | 1040 | 98.6 | 98.6 | 60.77 | 102544 | 63200.8 | 38.37% | 0% | 3.162% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Consultant / Developer | GD Offshore | GD Offshore10 | Development | GDC | Training Data | 1048 | 98.6 | 98.6 | 60.77 | 103332.8 | 63686.96 | 38.37% | 0% | 3.187% | 8 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Consultant / Developer | GD Offshore |  |  |  |  | 500 | 90 | 90 | 53.8867 | 45000 | 26943.3346 | 40.13% | 0% | 1.388% | 2026-07-13: 40; 2026-07-20: 40; 2026-07-27: 40; 2026-08-03: 40; 2026-08-10: 40; 2026-08-17: 40; 2026-08-24: 40; 2026-08-31: 40; 2026-09-07: 40; 2026-09-14: 40; 2026-09-21: 40; 2026-09-28: 40; 2026-10-05: 20
|  | Consultant / Developer | GD Offshore | GD Offshore11 | Development | GDC | Training Data | 1040 | 99.6 | 99.6 | 61.77 | 103584 | 64240.8 | 37.98% | 0% | 3.194% |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Intune - SECURITY | 0%
|  | Security Architect | Security Architect | Security Architect | Security | US |  | 0 | 462.8 | 462.8 | 418.3 | - | - | - | 0% | 0%
|  | Sr. Consultant (Intune) | Security Consultant | Senior Consultant2 | Security | US | Azure/Intune | 0 | 416 | 416 | 265.12 | - | - | - | 0% | 0%
|  | Security Consultant | GD Offshore | GD Offshore3 | Security | GDC | Intune | 0 | 93.6 | 93.6 | 55.77 | - | - | - | 0% | 0%
|  | Security Consultant | GD Offshore | GD Offshore3 | Security | GDC | Identity/AI | 0 | 93.6 | 93.6 | 55.77 | - | - | - | 0% | 0%
|  | Security consultant | Security Consultant | Security Consultant | Security | US | Identity/AI | 0 | 416 | 416 | 265.12 | - | - | - | 0% | 0%
|  | DCPS | 0.9569%
|  | DSA | Domain Solution Architect |  | Security |  | SBD | 39 | 421.2 | 421.2 | 418.3 | 16426.8 | 16313.7 | 0.6885% | 0% | 0.5066% | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | GD offshore cons | GD Offshore |  | Security |  | SBD | 156 | 93.6 | 93.6 | 55.77 | 14601.6 | 8700.12 | 40.42% | 0% | 0.4503% | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 2 | 2 | 2
Note on C4: Jeffrey Rosen: default is 3% leave cell blank/empty unless you intend for uplift. If week to start FY uplift is blank, the % will apply for all weeks.
Note on C5: Jeffrey Rosen: Just use a number, e.g. 10 to start the uplift applying in week 10 to the end. Leave cell blank to not apply uplift.
Note on F6: Jeffrey Rosen: If cell is Red, this indicates insufficient capacity vs estimated capacity
Note on B14: Typical estimate is 2k per person per week * # trips
Note on B15: 7% Std, 14% High
Note on E18: WHO: Architect Description: Purpose of this column is to map roles to physical resources. For example, you may have the Project Manager and Scrum master with the same role title, use this field to map them to indicate they are the same individual.
Note on G18: WHO: Architect Description: Indicates when we need to identify partner resources to generate a partner allocation caculation.
Note on H18: WHO: Architect Description: The purpose of this column is to provide general notes outside the GRM skills, however, leverage the "Resource Skills" worksheet to indicate the specific GRM skills required for the individual.
Note on K18: WHO: Pursuit Lead Description: The amount we charge the client per hour of work. Defaults to List Rate, but if there is a discount, apply the discounted bill rate here and override the default assignment to the List Rate.
Note on R22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Modified from 0
Note on C27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this row be blank?

## ACR (hidden)
2027–2032 Deployment Ramp (Bosch Volume Forecast)
Year | Total Vehicles | Wtd Avg ACR/Vehicle | Total ACR ($) | China ACR | Germany ACR | Japan ACR | US ACR
Year | Total Vehicles | Wtd Avg ACR/Vehicle | Total ACR ($) | China ACR | Germany ACR | Japan ACR | US ACR
2027 | 30000 | 111.7445 | 3352335 | 3352335 | 0 | 0 | 0
2028 | 510000 | 111.7445 | 56989695 | 16761675 | 29053570 | 11174450 | 0
2029 | 875500 | 111.7445 | 97832309.75 | 27936125 | 55872250 | 11174450 | 2849484.75
2030 | 1924500 | 111.7445 | 215052290.25 | 44697800 | 83808375 | 44697800 | 41848315.25
2031 | 2342500 | 111.7445 | 261761491.25 | 44697800 | 83808375 | 53637360 | 79617956.25
2032 | 2585000 | 111.7445 | 288859532.5 | 40228020 | 83808375 | 53637360 | 111185777.5
6-yr Cumulative | 8267500 |  | 923847653.75 | 177673755 | 336350945 | 174321420 | 235501533.75

## SkillList (hidden)
.NET API
.NET Framework
3D Modeling and Animation
3-Horizon Roadmap Development
3rd-party platform security and cybersecurity solutions
Access Control
Access Package Definition and Configuration
Accessibility
Active Directory Federation Services (ADFS)
Adaptive Grammar Engine (AGE/NADM)
Adoption Change Management (ACM)
Advanced Machine Learning Techniques
Advanced Threat Analytics (ATA)
Agent Coach
Agile
AI Operationalization and Governance
AI Solutions Development and Testing
AI test planning and execution
AJAX
Algorithmic Thinking
Android
Angular
Apache Axis
Apache Cassandra
Apache CXF
Apache Spark
Apache Tomcat
Apple iOS
Application Gateway
Application Packaging
Application Performance Assessment
Application Security
ArgoCD
Artifactory (JFrog)
Aspect CSS
Aspect CSS CTI
Assessment Services
Asterisk
ATOaaS
Audio processing/editing/directing
Augmented Reality (AR) Development
Authentication
Automated Build Pipeline Configuration
Automated Release Pipeline Configuration
Automation and Orchestration
Automation testing
Automation Testing using EasyRepro framework, Selenium and C#
Avaya AES (CTI)
Avaya Aura Communication Manager
Avaya Dialog Designer
Avaya IC (CTI)
Avaya Interactive Response (IR)
Avaya Orchestration Designer (AODD)
Avaya Voice Portal (AVP)
Azure - Govern and Manage
Azure - Govern and Manage
Azure Active Directory B2C
Azure AD Application Proxy
Azure Advance Networking (AAN)
Azure AI Studio
Azure Analysis Services
Azure API Management
Azure App Service
Azure Application Infrastructure
Azure Application Insights
Azure Applied AI Services
Azure Arc
Azure Arc-enabled Data Services
Azure Backup
Azure Bastion
Azure Bicep
Azure Bot Services
Azure Cloud Services
Azure Cognitive Search
Azure Cognitive Services
Azure Communication Services​
Azure Components
Azure Container Apps
Azure Cosmos DB
Azure Cost Management
Azure Data Catalog
Azure Data Explorer
Azure Data Factory
Azure Data Lake
Azure Data Lake Analytics
Azure Data Lake Storage
Azure Database for MySQL
Azure Database for PostgreSQL
Azure Database Migration Service
Azure Databricks
Azure DDoS Protection
Azure DevOps (ADO)
Azure DevOps Solutions for Cloud Infrastructure
Azure Digital Twins
Azure DNS
Azure Eventhub
Azure ExpressRoute
Azure Firewall
Azure Functions
Azure Governance and Management
Azure Health Bot
Azure IaaS
Azure Infrastructure
Azure Infrastructure Management
Azure IoT
Azure IoT Central
Azure IoT Edge
Azure IoT Hub
Azure Key Vault
Azure Kubernetes Service (AKS)
Azure Landing Zone
Azure Log Analytics
Azure Logic Apps
Azure Machine Learning
Azure Migrate
Azure Monitor
Azure Monitoring and Analytics
Azure Network Security
Azure Networking
Azure OpenAI
Azure OpenAI - Govern and Manage
Azure Performance and Scalability​
Azure Portal Management
Azure Quantum Elements platform
Azure Queue Storage
Azure Resource Manager (ARM)
Azure Security
Azure Security Benchmark
Azure Services
Azure Site Recovery
Azure Spring Apps
Azure SQL Database
Azure SQL Managed Instance
Azure Stack
Azure Stack HCI
Azure Storage
Azure Storage Accounts
Azure Stream Analytics
Azure Synapse
Azure Table Storage
Azure Threat Protection
Azure Virtual Desktop (AVD)
Azure Virtual Machines
Azure VMware Solution
Azure Web App Firewall
Azure Workbooks
Barge in Modes
Batch File Migrations
BeVocal Configuration Services (BCS)
Bitlocker Design and Implementation
BizTalk Server
Blockchain Architecture and Development
Blue Prism
Bookings
BR 3.0 (NDEP Business Rules)
Brew/BrewMP
Business Analytics
Business Case Development
Business Continuity
Business Decision Making
Business escalations
Business Objects
Business presentations
Business Strategy
Business Value Assessment
Business writing
C#
C++
Call Steering Tuning
Canvas Apps
Capability and Journey Mapping​
CAST Highlight
Certificate Services
Change Management
Cisco Call Studio
Cisco CTI
Cisco CVP
Cisco ICM Scripting
Cisco UCCE
Cisco UCCX
Citrix
Clickstream Data Analysis
Client / Customer QBR Support
Cloud Adoption Framework (CAF)
Cloud Applications
Cloud Database Architecture
Cloud Endpoint
Cloud Identity Services
Cloud Identity Services B2B
Cloud Identity Services B2C
Cloud Infrastructure
Cloud Infrastructure & Management
Cloud Management Gateway (CMG)
Cloud Monitoring for Azure Planning and Enablement
Cloud Monitoring for M365 Planning and Enablement
Cloud Workload Protection​
Clustering
Coaching
Cognos
Combined Engineering
Commercial Licensing
Common Data Model (CDM)
Competitor Analysis
Complex Multi-Domain Project Management
Compliance Management Product/ Solution​
Compliance testing
Compromise Recovery
Compute
Computer Vision
Conditional Access and Multi-Factor Authentication (MFA)
Conduct a Comprehensive Security Project Review
Configuration
Confluence
Connected Vehicle API Management
Connected Vehicle Data Management
Connected Vehicle Dynamics 365
Connectors
Console Application
Containerization and Orchestration
Continuous Collaboration
Continuous Improvement & Quality
Continuous Integration/Continuous Delivery (CI/CD)
Continuous Integration/Continuous Deployment
Continuous Operations and Monitoring
Continuous Planning
Continuous Security
Continuous Strategy and Product Planning
Conversational AI
Conversational AI system log processing
Copilot GPT Builder
Copilot Studio
Core Mobile Dictation (CMD)
Cortana Integrated Solutions
Cost Management Planning and Enablement
CPR (prompt library)
CRM Configuration
CRM Consulting Experience
CRM Data Architecture
CRM Developer Core Skill
CRM Enterprise Aplication Services (EAS)
CRM Functional Consulting
CRM Infrastructure Planning
CRM Integrations
CRM Power Suite
CRM Project Reviews & Assessments
CRM Security and Compliance
CRM Technical Consulting
Cross-Cloud Governance
Cross-Cloud Management and Support
Cross-Cloud Operating Model
Cross-Functional Collaboration
Cryptography
CSS
Culture and Cloud Service Model
Culture Change for AI & Copilot
Custom Code Container
Customer and Community Engagement
Customer Capability
Customer collaboration
Customer Data Platform - Customer Insights
Customer Data Platform - Customer Voice
Customer Experience Assessment & Optimization
Customer-First / Opportunity Analysis
Cybersecurity Architecture
Cybersecurity Strategy, Policies and Governance
DALL-E
Data Analysis and Exploration
Data and analytics
Data Collectors
Data Engineering
Data entities
Data governance
Data Governance and Operations
Data Landing Zone
Data Management and Integrity for Exchange Server Implementations and Migration
Data Mining
Data Model Evaluation
Data Modeling
Data operations
Data Platform Architecture and Analysis
Data Preparation and Understanding
Data Science
Data Science Deployment Technologies
Data Science Frameworks
Data Science Toolkit implementation
Data Warehouse
Dataverse
DB2
Deal Crafting / Proposal
Deal Orchestration
Debugging Tools
Deep Learning
Deliver Presentations
Deliver Projects using Secure DevOps Kit
Delivery Advisory
Delivery compliance
Delivery Excellence
Delivery Governance
Delivery Leadership
Delivery Orchestration
Delivery Oversight
Demand Generation
Demilitarized Zone (DMZ)
Deployment
Design Access Management
Design Fiction
Design Identity Management
Design of Experiments
Design Solution
Design Thinking
Develop High-level Digital Transformation Roadmap​
Develop New Business Models​
Develop Solution Options to Achieve Business Transformation​
Developer Services
Developer Tools
Development on Secure Infrastructure
DevOps Experience / Mindset
DevOps tool integrations
Dialed Number Manager (DNM)
Dialogic APIs
Difficult conversations
Digital Culture Change
Digital Optimization
Digital Storytelling
Digital Twins Design and Development
Digital Twins Model and Graph
Digital Voice and Video (DVV)
Directed Dialogue Tuning
DirectX
Distributed File System (DFS)
Distributed Systems and Networking
Distributed Systems and Networking for Blockchain
Docker
Docker Compose
Dragon Mobile SDK
Dynamics 365 Commerce: Business to Business (B2B) Implementation
Dynamics 365 Commerce: Connected Spaces Implementation
Dynamics 365 Commerce: Fraud Protection Implementation
Dynamics 365 Commerce: Point of Sale (POS) Implementation
Dynamics 365 Commerce: Retail Store Operations Implementation
Dynamics 365 Customer Data Platform: Customer Insights Implementation
Dynamics 365 Customer Data Platform: Customer Voice Implementation
Dynamics 365 Customer Engagement (CE)
Dynamics 365 Customer Service
Dynamics 365 Customization and Configuration
Dynamics 365 Finance
Dynamics 365 Finance and Operations (F&O)
Dynamics 365 Finance: Accounts Payable Module Implementation
Dynamics 365 Finance: Accounts Receivable Module Implementation
Dynamics 365 Finance: Budgeting Module Implementation
Dynamics 365 Finance: Cash and Bank Management Module Implementation
Dynamics 365 Finance: Consolidations
Dynamics 365 Finance: Consolidations Implementation
Dynamics 365 Finance: Cost Management (Accounting) Module Implementation
Dynamics 365 Finance: Credit & Collections Module Implementation
Dynamics 365 Finance: Currency Module Implementation
Dynamics 365 Finance: Enterprise Asset Management (EAM) Module Implementation
Dynamics 365 Finance: Expense Management Module Implementation
Dynamics 365 Finance: Fixed Assets Module Implementation
Dynamics 365 Finance: General Ledger Module Implementation
Dynamics 365 Finance: Intercompany Module Implementation
Dynamics 365 Finance: Landed Cost Module Implementation
Dynamics 365 Finance: Project Management & Accounting Module Implementation
Dynamics 365 Finance: Project Operations
Dynamics 365 Finance: Public Sector Implementation
Dynamics 365 Finance: Rebate Management Module Implementation
Dynamics 365 Finance: Tax Module Implementation
Dynamics 365 Human Resources (HR) Implementation
Dynamics 365 Marketing
Dynamics 365 Marketing: Adobe Marketing Cloud Implementation
Dynamics 365 Marketing: Marketing Insights Implementation
Dynamics 365 Plugins
Dynamics 365 Power Platform
Dynamics 365 Sales
Dynamics 365 Sales Implementation
Dynamics 365 Sales: Demand Forecasting Implementation
Dynamics 365 Sales: Microsoft Relationship Sales Implementation
Dynamics 365 Sales: Sales Insights Implementation
Dynamics 365 Sales: Sales Order Forecasting Module Implementation
Dynamics 365 Service: Connected Field Service (IoT) Implementation
Dynamics 365 Service: Customer Service Insights Implementation
Dynamics 365 Service: Customer Service Module Implementation
Dynamics 365 Service: Field Service Mobile Module Implementation
Dynamics 365 Service: Field Service Module Implementation
Dynamics 365 Service: Omni-channel Implementation
Dynamics 365 Service: Project Operations Implementation
Dynamics 365 Service: Remote Assist Module Implementation
Dynamics 365 Service: Service Agreements Module Implementation
Dynamics 365 Service: Unified Service Desk Module Implementation
Dynamics 365 Service: Virtual Agent for Customer Service Module Implementation
Dynamics 365 Supply Chain Management
Dynamics 365 Supply Chain Management (SCM): Advanced Warehousing Implementation
Dynamics 365 Supply Chain Management (SCM): Discrete Manufacturing Implementation
Dynamics 365 Supply Chain Management (SCM): Guides Implementation
Dynamics 365 Supply Chain Management (SCM): Intelligent Order Management (IOM) Implementation
Dynamics 365 Supply Chain Management (SCM): Intercompany Implementation
Dynamics 365 Supply Chain Management (SCM): Inventory Management Module Implementation
Dynamics 365 Supply Chain Management (SCM): Landed Cost Module Implementation
Dynamics 365 Supply Chain Management (SCM): Lean Manufacturing Module Implementation
Dynamics 365 Supply Chain Management (SCM): Master Planning Module Implementation
Dynamics 365 Supply Chain Management (SCM): Process Manufacturing Module Implementation
Dynamics 365 Supply Chain Management (SCM): Procurement & Sourcing Module Implementation
Dynamics 365 Supply Chain Management (SCM): Production Control Module Implementation
Dynamics 365 Supply Chain Management (SCM): Supply Chain Insights Implementation
Dynamics 365 Supply Chain Management (SCM): Transportation Management (TMS) Implementation
Dynamics 365 Supply Chain Management (SCM): Vendor Collaboration Module Implementation
Dynamics 365 Supply Chain Management (SCM): Warehouse Management (WMS) Module Implementation
Dynamics AX
Dynamics Copilot
Dynamics CRM
EAS Cloud Applications
EasyMock
EclEmma
Eclipse
eDiscovery
Emotional intelligence
Engagement Leadership
Enhanced Mitigation Experience Toolkit (EMET)
Enterprise Resource Planning (ERP) System
Enterprise Web architectures
Envisioning
Envisioning Workshop
Envoy
ERP Configuration
ERP Consulting Experience
ERP Functional Consulting
ERP Infrastructure Planning
ERP Integrations
ERP Security and Compliance
ERP Technical Consulting
Exchange Online Administration and Governance
Exchange Online Security and Compliance
Exchange Server
Exchange Server Development
Exchange Server Hybrid Design and Implementation
Exchange Server Notes Migration
Exchange Server Online Administration and Governance
Exchange Server Online Design and Implementation
Exchange Server Online Protection
Exchange Server Online Security and Compliance
Exchange Server On-Premises Design and Implementation
Exchange Server On-Premises to Online Migration
Exchange Server Tenant to Tenant Migration
Executive Presence
Executive Relationships
Expectation management
Fabric Copilot
Feature Team Engineering
Fiddler
Financial Analysis
FinOps
Flood Testing Tool
Fluentd
Forecasting
Forefront Identity Manager (FIM)
Forensic analysis tool
Forensic Analysis Tool​
Forms
Fraud Analytics
FSLogix
FSLogix Design and Implementation
Functional AI test planning and execution
Functional and Experience Benchmarking
Functional Security testing
Gatekeeper v1
Gatekeeper v2 Integration - gRPC APIs
Gatekeeper v2 Integration - REST APIs
Gatekeeper v2 Media Manager Integration- gRPC APIs
General Web Site development
Generative AI
Genesys Composer/Studio
Genesys CTI
Genesys GVP
Genomics Analytics
Git Lab- source control CI/CD
GitHub
GitHub - Copilot
GitHub Advanced Security
Github- source control CI/CD
GK2 Caller Validation Connector
GK2 Connectors deployment (hosted)
GK2 Connectors deployment (on-prem)
GlassFish
Golang (Go)
Google Cloud
Google Web Toolkit (GWT)
Governance Compliance
Governance Risk
GPU Compute Shaders
Graph API for M365
Graphical User Interface Design
Groovy
gRPC Framework
H.323 Telephony Architecture
H2 Database
Hadoop
Hardware Engineering
HD Insights
Helm
Hibernate Persistence Framework
High Performance Computing (HPC)
High-Level Shader Language (HLSL)
HockeyApp
Holly Voice Platform
HoloLens
Host configuration review
HR and Tech Domain Experience
HTML
HTTPS (SSL)
HttpUnit
Hudson
Hybrid & Multi-Cloud​
Hybrid Cloud Printing
Hybrid Cloud Well-Architected Framework
Hyper-V
iBatis Persistance Framework
IBM WebSphere
IBM WebSphere Voice Response
ICM Connector Installation
Identity & Access
Identity and Access Management Product/ Solution​
Identity Management
Identity Strategy
Incident Management
Incident Response
Inclusive Design
Inclusive Leadership
Industry Operational Excellence
Industry-Specific Analytics
Influencing Stakeholders
Information Protection
Infrastructure and Application Management
Infrastructure as a Service (IaaS)
Infrastructure as Code (IaC)
Infrastructure as Code (IaC) assets and tooling
Infrastructure Project Validation
Insightful Listening
Insight-Led Conversations
Insomnia
Intellectual Property (IP) Data Replicator
Intelligent Offer Management (IOM)
IntelliJ
Interactive Intelligence (I3) Platform
Interdisciplinary Expertise
Internet Information Services (IIS)
Internet Security Acceleration (ISA)
Interoperability
Intervoice (non-VXML)
Intervoice InVision
Intervoice MTC
Intervoice MTC CTI
Intune Application Protection
Intune Device Management​
IoT Application Management
IoT SDKs/RTOS
IQ Studio
IT & Business Strategy Alignment
J2EE (advanced)
J2ME
Jaeger
Java
JavaScript
Jboss Application Server
Jenkins
Jetty
Jira
JMeter
Jquery
JSON
JSUnit
Junit
Kanban
Kingsway Soft
Klaxoon
Knowledge Management
Knowledge Mining
Kusto Query Language (KQL)
Large Language Model
LDAP Authentication
Lean IT
Leverage Digital Signals
Linux
Live Chat Operational Metrics
Live Chat Program Design
Load balancing and Traffic Management
Local Administrator Password Solution (LAPS)
M365 - Govern and Manage
M365 Copilot
MaaS Assessment Services
Machine Learning and Modeling
Machine Learning Ops (ML Ops)
Macros
Mainframe Modernization Services
Managed IP Development
Managed Services and IP Development
Manual Testing of D365 solution and Integrations
Market and Customer Understanding
Marketing - Adobe Marketing Cloud
Marketing - Marketing Insights
Marketing Analytics
Maven
Meego
Mentimeter
Mercurial
Metaverse
Microsoft 365 Administration and Governance
Microsoft 365 Administration Center
Microsoft 365 Advanced Data Loss Prevention (DLP) Design and Implementation
Microsoft 365 Defender
Microsoft 365 Enterprise Apps (Office)
Microsoft 365 Enterprise Mobility + Security (EMS)
Microsoft 365 for Education
Microsoft 365 General
Microsoft 365 Identity
Microsoft 365 Information Governance Design and Implementation
Microsoft 365 Integration for Virtual Personal Assistant (VPA)
Microsoft 365 Management API
Microsoft 365 Network Performance and Optimization
Microsoft 365 Scripting
Microsoft 365 Store
Microsoft 365 Suite
Microsoft Application Management
Microsoft Application Packaging Design and Implementation
Microsoft Azure Integration Services
Microsoft Bookings
Microsoft Catalyst
Microsoft Certificate Solutions
Microsoft Cloud App Security (MCAS)
Microsoft Cognitive Toolkit (CNTK)
Microsoft Commerce Server
Microsoft Configuration Manager
Microsoft Defender Cloud Security Posture Mgmt
Microsoft Defender External Attack Surface Management
Microsoft Defender for Business
Microsoft Defender for Cloud
Microsoft Defender for DevOps
Microsoft Defender for Endpoint
Microsoft Defender for Identity
Microsoft Defender for IoT
Microsoft Defender for Microsoft 365
Microsoft Defender for Office 365
Microsoft Defender Threat Intelligence (MTDI)
Microsoft Defender Vulnerability Management
Microsoft Delve
Microsoft Device Analytics Design and Implementation
Microsoft Dynamics Lifecycle Services (LCS)
Microsoft Endpoint Configuration Manager
Microsoft Entra External ID
Microsoft Entra ID (Azure AD)
Microsoft Entra ID Governance
Microsoft Entra ID Protection
Microsoft Entra Internet Access – Public Preview
Microsoft Entra Permissions Management
Microsoft Entra Private Access – Public Preview
Microsoft Entra Strong Authentication
Microsoft Entra Verified ID
Microsoft Entra Workload ID
Microsoft Fabric
Microsoft GCC
Microsoft GCC-High
Microsoft Identity Manager (MIM)
Microsoft IIS
Microsoft Intune
Microsoft Intune App Protection Design and Implementation
Microsoft Intune Endpoint Privilege Management​
Microsoft Intune Mobile Device Management (MDM) Design and Implementation
Microsoft Loop
Microsoft Priva
Microsoft Priva Risk Management
Microsoft Priva Subject Rights Requests
Microsoft Project Design and Implementation
Microsoft Project Development
Microsoft Project Migration
Microsoft Purview
Microsoft Purview Audit
Microsoft Purview Communication Compliance
Microsoft Purview Compliance Manager
Microsoft Purview Data Catalog
Microsoft Purview Data Estate Insights
Microsoft Purview Data Lifecycle Management
Microsoft Purview Data Loss Prevention
Microsoft Purview Data Map
Microsoft Purview eDiscovery
Microsoft Purview for M365
Microsoft Purview Information Governance
Microsoft Purview Information Protection
Microsoft Purview Insider Risk Management
Microsoft Remote Assist
Microsoft Sales Process
Microsoft Search
Microsoft Security Copilot
Microsoft Security Frameworks and Reference Architectures​
Microsoft Sentinel
Microsoft SQL Server Reporting Services
Microsoft Store for Business
Microsoft Stream
Microsoft Sustainability Manager
Microsoft Syntex
Microsoft Teams
Microsoft Tunnel Design and Implementation
Microsoft Viva
Microsoft Viva Change Management
Microsoft Viva Design and Implementation
Microsoft Whiteboard
Migration and Optimization
Migration Testing
Mix.dialog
Mix.nlu
Mixed Reality
Mobile App Development
Mobile Testing
Mobile User Interface Design
MobileSDK (NDEP)
Mockito
Model Deployment and Evaluation
Model Driven Apps
Modeling and Statistical Analysis
Modeling Experience
Modern Service Management (MSM)
MQ Series
Multi-Industry Experience
Multilingual design
Mural
MXML
Name Resolution
Native
Natural Language Processing
Natural Language Understanding (NLU) - Design
Natural Language Understanding (NLU) - Tagging
NDEP Chat Interface v2 (CIV2)
NEAP/Mix Nuance Insights
Negotiation
NetBeans
Network and Remote Access​ Security Management
Network deployment and customization
Network Design and Implementation
Network Management and Monitoring
Networking
Nginx
NICE Call Recording
Nina Virtual Assistant
NOD mock backend
NOD Voice Ruby
Node and package management via NPM​
Node.js
Nortel MPS
Nortel PeriPro
NoSQL Database
Notification Hub
Nuance Agent Interface
Nuance Application Reporting (NAR)
Nuance Application Studio (NAS)
Nuance Automation Assist
Nuance Call Steering Portal (NCSP)
Nuance Client Portal (NCP)
Nuance Conversation Engine (NCE)
Nuance Development Framework - Regular (NDF)
Nuance Development Framework - State Engine (NDF SE)
Nuance Dialog Module (NDM)
Nuance Digital Engagement Platform (NDEP)
Nuance Enterprise Access Management (NEAM)
Nuance Enterprise Studio (NES)
Nuance FreeSpeech
Nuance Insights for IVR (NII)
Nuance Krypton
Nuance Language Engine (NLE)
Nuance License Manager (FlexLM)
Nuance Management Station (NMS)
Nuance Mix
Nuance Mobile Application Server (NMAS) development
Nuance Mobile Speech Platform (NMSP) SDK
Nuance Natural Language Engine (NLE)
Nuance Proactive Engagement Platform (NPEP)
Nuance Resource Manager (NRM)
Nuance Speech Server (NSS) 5.x, 6.x
Nuance Stubbing Framework (nStubs)
Nuance Vocalizer for Cloud (NVC) SDK
Nuance Voice Portal (NVP)
Objective-C
Objectives and Key Results (OKRs)
Obstacle removal
OICD - Azure Open ID Connect
Omni-Channel
On Demand Insight (ODI)
Onboarding Pack Solution Security
OneDrive for Business
On-Premises Identity Services
Open Source Container Orchestration
Open Source Solutions
Open Speech Attendant (OSA)
OpenSpeech Dialog (OSD)
OpenSpeech Dialog Modules (OSDM)
OpenSTA
Operations for Artificial Intelligence & Copilot
Operations for Machine Learning
Opportunity and Solution Identification
Opportunity Identification
Opportunity Qualification
Optimization
Oracle
Oracle GoldenGate
Oracle Weblogic Application Server
Orchestration
Org and Technical Assessment
Organizational Transformation and Change
OT Protocols
Outbound IVR or Outbound SMS
Pentaho
People Mobilization for Velocity Services
PeopleSoft
Performance and Troubleshooting
Performance Optimization
Perl
PHP
Pipeline Forecasting
Platform as a Service (PaaS)
Portfolio Management
Postman
Power Apps
Power Apps Component Framework
Power Automate
Power BI
Power Pages
Power Platform - Govern and Manage
Power Platform Copilot
Power Portals
Power Virtual Agents
PowerShell
Predictive Modeling
Prioritization
Privileged Access Workstation (PAW​)
Privileged Access Workstation for Cloud Services Management (PAW CSM)
Problem Solving
Process Automation Development
Product backlog management
Product Centric Experience
Product manager support
Product OKR Definition​
Product Planning and Roadmapping
Product Strategy and Vision
Product/ Service Advocacy
Product/ Service Design
Product/ Service Launch Facilitation
Product/ Service Monitoring and Evaluation
Program Management
Programming Logic
Project Communications Management
Project Cost Management
Project Integration Management
Project Management and Coordination for Exchange Server Implementations and Migration
Project Pre-Sales/Capture Management
Project Procurement Management
Project Quality Management
Project Recovery Assessment Planning
Project Recovery Conduct Assessment
Project Recovery Execution
Project Recovery Plan Development
Project Recovery Process
Project Recovery Root Cause Analysis
Project Resource Management
Project Risk Management
Project Scope Management
Project Time Management
Prometheus
Prompt Flow
PROSCI
Public Key Infrastructure (PKI)
Puppet
Python
Quality Assurance
Quality Assurance (QA)
Quantum Algorithms
Quantum Computing
Quantum Hardware Interface
R
Rapid Prototyping
React
RealSpeak 4.0/4.5
Recognize and Respond to Security Threats​
Recurring Integrations Scheduler (RIS)
REDIS Cache
Regulatory Compliance
Repeat Caller Analysis
Repeat Contact Analysis
Report Creation & Customization
Reporting KPI definition (Key Performance Indicators)
Researching stakeholders
Resin
Resource Manager (NRM)
Resource Planning
Responsible AI
Retail Server/CRT Extension/ Retail SDK​
Rights Management Services (RMS)
Risk & Credit Analytics
Risk Management​
RiverMeadow
Robotic Process Automation (RPA)
Robotic Process Automation (RPA) Migration Tools
SAAS Solutions
SAFe – The Scaled Agile Framework
SAGE Box (T-1 Test tool)
SAP Data Services
SAP Hana Cloud Integration
SAP Hana Cloud Platform
SAP Landscape Transformation
SAP on Azure
SAP Project Management
SAP Rise on Azure
Scala
Scribe
Scripting
SCRUM
Scrum@Scale
SCSS for theme development (or CSS)​
Search Capabilities
Secure Control Framework (SCF)
Secure Development
Secure Hybrid Identities​
Secure Management​
Security and Compliance Center (SCC)
Security and Governance
Security Architecture
Security Architecture​
Security code review
Security Compliance
Security Development Lifecycle process (SDL)
Security for Endpoint​
Security Incident Management and Crisis Management
Security Information and Event Management (SIEM​)
Security Investigations
Security Operating Model Adoption for Digital Security and Compliance
Security Operations
Security Operations (Security Operating Model)​
Security testing
Security Threat Analysis
Security Threat Investigation
Sell-with partners
Serverless Computing
Service Usage Report (SUR)
Services Management for Azure
Services Management for CCoE Cloud Native Operations
Services Management for D365 Operational Readiness
Services Management for Data Governance and Operations
Services Management for Information Protection and Governance
Services Management for Intune Device Management
Services Management for Microsoft 365
Services Management for Privileged Access Workstation
Services Management for Security Operating Model for Identity
Services Management for Security Operating Model for SOC
Session Initiation Protocol (SIP)
SharePoint
SharePoint Administration
SharePoint Development
SharePoint Hybrid Design and Implementation
SharePoint Online Administration and Governance
SharePoint Online Custom Development
SharePoint Online Design and Implementation
SharePoint Online Modern Experiences
SharePoint On-Premises Design and Implementation
SharePoint On-Premises to Online Migration
SharePoint Search Design and Implementation
SharePoint Server
SharePoint Syntex
SharePoint Tenant-to-Tenant (T2T) Migration
Simulation
Single Sign-On (SSO)
Situational Fluency
Six Sigma
Skype for Business Design and Implementation
Skype for Business Development
Skype for Business Server
Skype for Business to Teams Migration
Skype for Business with Voice Design and Implementations
SOAP UI
Software Defined Datacenter
Software Engineering
Solution Demonstration
Solution Play Expertise
Speaker Verification Password Reset
Speech Secure 3.1
SpeechWorks Media Server (SWMS/MRCP) 3.0
Speechworks Voice Framework (SVF)
Spring
Spring Boot
SQL Clustering
SQL Server Integrated Services (SSIS)
SQL Server on Virtual Machines
SQL Server On-Premise
SQL Server Queries and Stored Procedures
SSL Certificates
Stakeholder Management
Stakeholder Mapping
Stateless Device Design and Implementation
Statistical modeling
Storage configuration
Storytelling
Strategic Communication
Strategic Partnership
Strategic questioning
Strategic Thinking
StresStimulus
Structure AI Services to deliver business outcomes
Structure Data & AI Services
Subversion
Supply Chain Analytics
Support Sales GTMs
Sure Step 365 LED Agile
Sure Step 365 LED Iterative
SureStep 365
Surface
Sustainability
Sybase
System Center Data Protection Manager (DPM)
System Center Endpoint Protection
System Center Operations Manager (SCOM)
System Center Orchestrator (SCORCH)
System Center Service Manager (SCSM)
System Center Virtual Machine Manager (SCVMM)
Tableau
Target Operating Model Adoption and Communities
Target Operating Model Strategy and Enablement
Task Analysis
TCP/IP Networking Program
Team Building
Team Data Science Process
Team Organization
Teams Administration and Governance
Teams App Deployment and Management
Teams App Development
Teams Design and Implementation
Teams Enterprise Voice
Teams Media Health and Networking
Teams Meetings and Live Events
Teams Phone Calling Plans
Teams Phone Devices
Teams Phone Direct Routing
Teams Phone Operator Connect
Teams Phone System Foundation
Teams Rooms
Teams tenant to tenant Migration
Teams with Voice Design and Implementation
Technical Assessment
Technical Automation and Orchestration
Technical Communication
Technical Data Engineering
Technical Demonstrations
Technical Infrastructure Design
Technical Quality Assurance (TQA)
Technical Solution Architecture
Technical Test Planning and Execution
Technology Architecture
Technology Roadmapping
Telecommunication Analytics
Telecommunication Design and Deployment
Telematics
Terraform
Territory Planning
Test Automation and tooling
Thought Leadership
Threat Analysis
Threat Management
Threat Management Gateway (TMG)
Threat Modelling
Trade-off decisions
Traditional Windows Deployment Design and Implementation
Transportation Analytics
Tuning/Optimization
Typescript
UiPath
Understand your stakeholders
Unified Modelling Language
Unreal Engine
Usability testing
User story backlog decisions
UX - User Experience
UX .Net Client Development
UX Architecture Patterns and Frameworks
UX Azure Client-related Services Front end Development
UX Cross-platform UI Development
UX Design
UX Discovery
UX Discovery Focused Interviewing
UX Discovery Persona and Scenario Creation
UX Discovery User Journeys and Journey Mapping
UX Discovery User Research
UX Interaction Design Low-Fidelity Prototyping
UX Interaction Wireframes Design
UX Mobile App Development
UX Natural User Interface (NUI) Design
UX Prototyping in Unity 3D / Unity C# Scripting
UX Requirements
UX SharePoint Branding Development
UX Visual Accesibility Design
UX Visual Branding Design
UX Visual Design
UX Visual Design Style Guide Creation
UX Visual Design Visualization
UX Web Front-end Development
Verifier 4.x
Viecore Framework
Virtual Machine Deployment and Customization
Virtual Reality (VR)
Virtualization
Visual COBOL
Visual Studio
Viva Connections
Viva Engage
Viva Extensibility and APIs
Viva Goals
Viva Insights
Viva Learning
Viva Topics
Vocal Password
Vocalizer (TTS polishing)
Vocalizer 5.x
Vocalizer 6.x
Vocalizer Studio
Voice Biometrics
Voice of the Customer (VOC) Analytics (aka CallMiner)
Voice User Interface Design
VoiceGenie VG
VoiceXML
Voxeo Prophecy
VPN Gateway
Vsuite development
Waterfall Project Management (based on PMP)
Web App Development and Hosting
Web Development
Webhooks
WebSDK (NDEP)
Well Architected Framework (WAF)
Windows 10/11
Windows 11
Windows administration
Windows Application Remediation Design and Implementation
Windows AppLocker Design and Implementation
Windows as a Service (WaaS)
Windows Autopilot Design and Implementation
Windows Client
Windows Client (Pre-Windows 11)
Windows Client Security
Windows Copilot
Windows Defender
Windows Defender Application Control Design and Implementation
Windows Defender Solutions Design and Implementation
Windows Deployment
Windows Hello for Business
Windows Hello for Business Design and Implementation
Windows Information Protection
Windows Information Protection (WIP) Design and Implementation
Windows Server
Windows Server Failover Clustering
Windows Server File Services
Windows Server Security
Windows Server Update Services (WSUS)
Windows Servicing Design and Implementation
Windows Update for Business
Windows Virtual Desktop (WVD) Design and Implementation
WireMock
Wireshark (formally Ethereal)
Workshop planning and facilitation
WOZ testing
X++ Coding​
Xamarin Products
xCode
XHTML+VoiceXML (X+V)
XML
YAML Ain't Markup Language (YAML)
Yammer
Yammer Design and Implementation
Yammer Development
Zenoss
Zero Trust Framework​
Zero Trust Security Narrative

## Rates (hidden)
Role | Cost | List | TMZ | Area | Practice
Consultant | 186.8029 | 300 | Americas | United States | Commercial Sector
Consulting Product Manager | 188.458 | 330 | Americas | United States | Commercial Sector
Data Scientist | 360.6281 | 400 | Americas | United States | Commercial Sector
Delivery Management Executive | 458.1842 | 460 | Americas | United States | Commercial Sector
Domain Solution Architect | 404.1545 | 405 | Americas | United States | Commercial Sector
GD Offshore | 53.8867 | 90 | Americas | United States | Commercial Sector
GD Onsite | 233.3287 | 365 | Americas | United States | Commercial Sector
GitHub Services Delivery | 404.1545 | 490 | Americas | United States | Commercial Sector
GitHub Services PMO | 258.3668 | 370 | Americas | United States | Commercial Sector
Partner SE | 549.3779 | 750 | Americas | United States | Commercial Sector
Principal Data Scientist | 367.3109 | 500 | Americas | United States | Commercial Sector
Principal SE (IC) | 385.5336 | 500 | Americas | United States | Commercial Sector
Principal SE (Lead) | 403.1955 | 525 | Americas | United States | Commercial Sector
Program Architect | 461.1845 | 500 | Americas | United States | Commercial Sector
Program Director | 303.9709 | 425 | Americas | United States | Commercial Sector
Project Manager | 186.3254 | 305 | Americas | United States | Commercial Sector
Security Architect | 404.1545 | 445 | Americas | United States | Commercial Sector
Security Consultant | 256.1502 | 400 | Americas | United States | Commercial Sector
Senior Consultant | 256.1502 | 365 | Americas | United States | Commercial Sector
Senior Consulting Product Manager | 267.7035 | 380 | Americas | United States | Commercial Sector
Senior Domain Solution Architect | 404.1545 | 490 | Americas | United States | Commercial Sector
Senior Project Manager | 258.3668 | 370 | Americas | United States | Commercial Sector
Software Engineer (IC) | 295.584 | 400 | Americas | United States | Commercial Sector
Principal Technical Program Manager | 386.8262 | 525 | Americas | United States | Commercial Sector
Technical Program Manager | 328.4801 | 425 | Americas | United States | Commercial Sector

## Helper (hidden)
Delivery Management Executive | Delivery Management Executive1
Program Architect | Program Architect1
Senior Project Manager | Senior Project Manager1
GD Offshore | GD Offshore1 | GD Offshore2 | GD Offshore3 | GD Offshore4 | GD Offshore5 | GD Offshore6 | GD Offshore7 | GD Offshore8 | GD Offshore9 | GD Offshore10
GD Offshore | GD Offshore1 | GD Offshore2 | GD Offshore3 | GD Offshore4 | GD Offshore5 | GD Offshore6 | GD Offshore7 | GD Offshore8 | GD Offshore9 | GD Offshore10
0 | 01 | 02 | 03
0.25531 | 0.2553067233864671
Senior Domain Solution Architect | Senior Domain Solution Architect1
Senior Consultant | Senior Consultant1 | Senior Consultant2 | Senior Consultant3
GD Offshore | GD Offshore1 | GD Offshore2 | GD Offshore3 | GD Offshore4 | GD Offshore5 | GD Offshore6 | GD Offshore7 | GD Offshore8 | GD Offshore9 | GD Offshore10
GD Offshore | GD Offshore1 | GD Offshore2 | GD Offshore3 | GD Offshore4 | GD Offshore5 | GD Offshore6 | GD Offshore7 | GD Offshore8 | GD Offshore9 | GD Offshore10
GD Offshore | GD Offshore1 | GD Offshore2 | GD Offshore3 | GD Offshore4 | GD Offshore5 | GD Offshore6 | GD Offshore7 | GD Offshore8 | GD Offshore9 | GD Offshore10
GD Offshore | GD Offshore1 | GD Offshore2 | GD Offshore3 | GD Offshore4 | GD Offshore5 | GD Offshore6 | GD Offshore7 | GD Offshore8 | GD Offshore9 | GD Offshore10
0.40683 | 0.4068334245194291
Principal Data Scientist | Principal Data Scientist1
Data Scientist | Data Scientist1 | Data Scientist2 | Data Scientist3 | Data Scientist4
Data Scientist | Data Scientist1 | Data Scientist2 | Data Scientist3 | Data Scientist4
Data Scientist
Data Scientist
Senior Consultant
Senior Consultant
GD Offshore
GD Offshore
GD Offshore
GD Offshore
Security Architect
0
0
0.015086
Security Architect
Security Consultant

## Helper2 (hidden)
LaborCategory
Governance

## Helper3 (hidden)
Estimate Category
Infrastructure
AI
Development
Security
ASCM