## POST SRM (V2)
Area | Role | Area | Project Role | Location | Country | Partner | Bill Rate | Bill Total | Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
[10 empty] | Mobilize & Initiate |  | 3: Solution Modeling, Build, Test, & Deploy
[10 empty] | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 |  | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04
[10 empty] | 2 Weeks |  | 2026-07-27: 12 Weeks |  | 12 Weeks
Functional Support | Senior Consultant | AIBS | Functional Lead / Delivery Architect | Onshore | USA | Microsoft | 379.6 | 394784 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Senior Consultant | AIBS | Functional Consultant (Co-Pilot) | Onshore | USA | Microsoft | 379.6 | 0 | 0
Functional Support | [7 empty] | 394784 | 1040
Architecture Support | Domain Solution Architect | AIBS | Solution Architect - AIBS | Onshore | USA | Microsoft | 421.2 | 155001.6 | 368 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| Domain Solution Architect | IGD | Solution Architect - IGD | Offshore | India | Microsoft | 90 | 93600 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Domain Solution Architect | AIBS | Solution Architect - TQA | Onshore | USA | Microsoft | 421.2 | 0 | 0
| Senior Consultant | AIBS | Integration Architect | Onshore | USA | Microsoft | 379.6 | 42515.2 | 112 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Architecture Support | [7 empty] | 291116.8 | 1520
Development Support | Consultant | IGD | Lead Developer ( 50% Lead) | Offshore | India | Microsoft | 93.6 | 97344 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Copilot / Foundry Developer | Offshore | India | Microsoft | 93.6 | 89856 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Copilot / Foundry Developer | Offshore | India | Microsoft | 93.6 | 89856 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Power Automate Developer | Offshore | India | Microsoft | 93.6 | 89856 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Modern Apps Developer (HITL) | Offshore | India | Microsoft | 93.6 | 89856 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Data Engineer (Ingestion- Integration) | Offshore | India | Microsoft | 93.6 | 44928 | 480 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Domain Solution Architect | IGD | TQA | Offshore | India | Microsoft | 93.6 | 17971.2 | 192 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Consultant | IGD | Test Lead / Tester | Offshore | India | Microsoft | 93.6 | 89856 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Development Support | [7 empty] | 609523.2 | 6512
Infrastructure Support | Consultant | IGD | Infrastructure/Environment Support | Offshore | India | Microsoft | 93.6 | 29203.2 | 312 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| Consultant | IGD | Release Manager - Devops / LLMOps | Offshore | India | Microsoft | 93.6 | 26956.8 | 288 |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Infrastructure Support | [7 empty] | 56160 | 600
Project Delivery Support | Delivery Mgmt. Executive | AIBS | Delivery Management | Onshore | USA | Microsoft | 478.4 | 49753.6 | 104 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Senior Project Manager | AIBS | Program Director | Onshore | USA | Microsoft | 384.8 | 80038.4 | 208 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Senior Project Manager | AIBS | Onsite Project Manager | Onshore | USA | Microsoft | 384.8 | 400192 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Project Manager | IGD | Offshore Project Manager | Offshore | India | Microsoft | 93.6 | 97344 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Project Delivery Support | [7 empty] | 627328 | 2392
Delivery Compliance, Privacy and Security | Consultant | IGD | Infosec Consultant | Onshore | India | Microsoft | 93.6 | 9360 | 100 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Domain Solution Architect | TZ | Domain Solution Architect | Onshore | USA | Microsoft | 462.8 | 53684.8 | 116 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Delivery Compliance, Privacy and Security | [7 empty] | 63044.8 | 216
Adoption, Change and Services Management | Sr. Domain Solution Architect | ACM | ACSM Architect | Onshore | USA | Microsoft | 509.6 | 108035.2 | 212 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Senior Consultant | ACM | ACM Sr Con (Agent Adoption) | Onshore | USA | Microsoft | 379.6 | 212576 | 560 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Consultant | ACM | ACM Con (Demos) | Onshore | USA | Microsoft | 312 | 149760 | 480 |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Adoption, Change and Services Management | [7 empty] | 470371.2 | 1252
Security | Security Architect | EAG | AI Security Foundations | Onshore | USA | Microsoft | 462.8 | 120328 | 260 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Security Architect | EAG | Agentic SOC | Onshore | USA | Microsoft | 462.8 | 166608 | 360 |  |  | 2026-09-07: 20; 2026-09-14: 20; 2026-09-21: 20; 2026-09-28: 20; 2026-10-05: 20; 2026-10-12: 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Security Consultant | EAG | AI Security Foundations | Onshore | USA | Microsoft | 416 | 199680 | 480 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Security Consultant | EAG | Agentic SOC | Onshore | USA | Microsoft | 93.6 | 67392 | 720 |  |  | 2026-09-07: 40; 2026-09-14: 40; 2026-09-21: 40; 2026-09-28: 40; 2026-10-05: 40; 2026-10-12: 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Security Consultant | EAG | Agentic SOC | Onshore | USA | Microsoft | 416 | 216320 | 520 |  |  | 2026-09-07: 40; 2026-09-14: 40; 2026-09-21: 40; 2026-09-28: 40; 2026-10-05: 40; 2026-10-12: 40 |  | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Security Support | [7 empty] | 770328 | 2340
[5 empty] | TOTAL (MS) |  |  | 3282656 | 15872
[5 empty] | TOTAL (KPMG) |  |  | 555257.95
[5 empty] | TOTAL (ESWO) |  |  | 3837913.95 | 15872
[5 empty] | AIBS Portion (-Security) |  |  | 3067585.95 | 13532
[5 empty] | Delta |  |  | 67585.95
KPMG Prototype Use Case 1 | Program Dir | EAG | Fx-SME | Onshore | USA | KPMG | 578.5714 | 11571.4286 | 20 |  |  | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2
| Sr PM | EAG | AI-SME | Onshore | USA | KPMG | 418.5714 | 26788.5714 | 64 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Tech Consultant | EAG | Agent Delivery | Onshore | USA | KPMG | 357.1429 | 114285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Offshore Tech Consultant | EAG | Agent Delivery | Offshore | India | KPMG | 107.1429 | 34285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Offshore Tech Consultant | EAG | Agent Delivery | Offshore | India | KPMG | 107.1429 | 34285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Use Case 1 Support | [7 empty] | 221217.1429 | 1044
KPMG Prototype Use Case 2 | Security Architect | EAG | Fx-SME | Onshore | USA | KPMG | 578.5714 | 11571.4286 | 20 |  |  | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2
| Security Architect | EAG | AI-SME | Onshore | USA | KPMG | 418.5714 | 26788.5714 | 64 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Security Consultant | EAG | Agent Delivery | Onshore | USA | KPMG | 357.1429 | 114285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Security Consultant | EAG | Agent Delivery | Onshore | India | KPMG | 107.1429 | 34285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Security Consultant | EAG | Agent Delivery | Onshore | India | KPMG | 107.1429 | 34285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Use Case 2 Support | [7 empty] | 221217.1429 | 1044
[5 empty] | KPMG Total |  |  | 442434.2857 | 2088
[5 empty] | Travel |  |  | 58519.41
[5 empty] | TOTAL (ESWO + Travel) |  |  | 3896433.36 | 15872
Note on C31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to discuss if PD should have some hours in here.
Note on P41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Raj Goel - for the 2 agents and a limited group of 40 pilot users, hours can be reduced or are we establishing a champions network and building the strategy and plan they can use for future agents? Reply: Yes ACM team is activating champions network, that will be utilized for future agent adoption tasks, and an adoption strategy for agent adoption in addition to adoption of in-scope agents.

## POST SRM (V1)
Area | Role | Area | Project Role | Location | Country | Partner | Bill Rate | Bill Total | Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
[10 empty] | Mobilize & Initiate |  | 3: Solution Modeling, Build, Test, & Deploy
[10 empty] | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 |  | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04
[10 empty] | 2 Weeks |  | 2026-07-27: 12 Weeks |  | 12 Weeks
Functional Support | Senior Consultant | AIBS | Functional Lead / Delivery Architect | Onshore | USA | Microsoft | 379.6 | 394784 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Senior Consultant | AIBS | Functional Consultant (Co-Pilot) | Onshore | USA | Microsoft | 379.6 | 212576 | 560 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Functional Support | [7 empty] | 607360 | 1600
Architecture Support | Domain Solution Architect | AIBS | Solution Architect - AIBS | Onshore | USA | Microsoft | 421.2 | 155001.6 | 368 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| Domain Solution Architect | IGD | Solution Architect - IGD | Offshore | India | Microsoft | 93.6 | 97344 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Domain Solution Architect | AIBS | Solution Architect - TQA | Onshore | USA | Microsoft | 421.2 | 0 | 0
| Senior Consultant | AIBS | Integration Architect | Onshore | USA | Microsoft | 379.6 |  | 112 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Architecture Support | [7 empty] | 252345.6 | 1520
Development Support | Consultant | IGD | Lead Developer ( 50% Lead) | Offshore | India | Microsoft | 93.6 | 97344 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Copilot / Foundry Developer | Offshore | India | Microsoft | 93.6 | 89856 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Copilot / Foundry Developer | Offshore | India | Microsoft | 93.6 | 89856 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Power Automate Developer | Offshore | India | Microsoft | 93.6 | 89856 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Modern Apps Developer (HITL) | Offshore | India | Microsoft | 93.6 | 89856 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Data Engineer (Ingestion- Integration) | Offshore | India | Microsoft | 93.6 | 44928 | 480 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Domain Solution Architect | IGD | TQA | Offshore | India | Microsoft | 93.6 | 17971.2 | 192 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Consultant | IGD | Test Lead / Tester | Offshore | India | Microsoft | 93.6 | 89856 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Development Support | [7 empty] | 609523.2 | 6512
Infrastructure Support | Consultant | IGD | Infrastructure/Environment Support | Offshore | India | Microsoft | 93.6 | 29203.2 | 312 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| Consultant | IGD | Release Manager - Devops / LLMOps | Offshore | India | Microsoft | 93.6 | 26956.8 | 288 |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Infrastructure Support | [7 empty] | 56160 | 600
Project Delivery Support | Delivery Mgmt. Executive | AIBS | Delivery Management | Onshore | USA | Microsoft | 478.4 | 49753.6 | 104 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Senior Project Manager | AIBS | Onsite Project Manager | Onshore | USA | Microsoft | 384.8 | 400192 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Project Manager | IGD | Offshore Project Manager | Offshore | India | Microsoft | 93.6 | 97344 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Project Delivery Support | [7 empty] | 547289.6 | 2184
Delivery Compliance, Privacy and Security | Consultant | IGD | Infosec Consultant | Onshore | India | Microsoft | 93.6 | 9360 | 100 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Domain Solution Architect | TZ | Domain Solution Architect | Onshore | USA | Microsoft | 421.2 | 48859.2 | 116 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Delivery Compliance, Privacy and Security | [7 empty] | 58219.2 | 216
Adoption, Change and Services Management | Sr. Domain Solution Architect | ACM | ACSM Architect | Onshore | USA | Microsoft | 509.6 | 108035.2 | 212 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Senior Consultant | ACM | ACM Sr Con (Agent Adoption) | Onshore | USA | Microsoft | 379.6 | 212576 | 560 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Consultant | ACM | ACM Con (Demos) | Onshore | USA | Microsoft | 312 | 149760 | 480 |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Adoption, Change and Services Management | [7 empty] | 470371.2 | 1252
Security | Security Architect | EAG | AI Security Foundations | Onshore | USA | Microsoft | 460.58 | 119750.8 | 260 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Security Architect | EAG | Agentic SOC | Onshore | USA | Microsoft | 460.58 | 165808.8 | 360 |  |  | 2026-09-07: 20; 2026-09-14: 20; 2026-09-21: 20; 2026-09-28: 20; 2026-10-05: 20; 2026-10-12: 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Security Consultant | EAG | AI Security Foundations | Onshore | USA | Microsoft | 414 | 198720 | 480 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| IGD Offshore Security Consultant | EAG | Agentic SOC | Offshore | USA | Microsoft | 414 | 298080 | 720 |  |  | 2026-09-07: 40; 2026-09-14: 40; 2026-09-21: 40; 2026-09-28: 40; 2026-10-05: 40; 2026-10-12: 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Security Consultant | EAG | Agentic SOC | Onshore | USA | Microsoft | 414 | 215280 | 520 |  |  | 2026-09-07: 40; 2026-09-14: 40; 2026-09-21: 40; 2026-09-28: 40; 2026-10-05: 40; 2026-10-12: 40 |  | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Security Support | [7 empty] | 997639.6 | 2340
[5 empty] | TOTAL (MS) |  |  | 3598908.4 | 16224
[5 empty] | TOTAL (KPMG) |  |  | 482857.1429 | 2088
[5 empty] | TOTAL (ESWO) |  |  | 4081765.5429 | 18312
[5 empty] | AIBS Portion (-Security) |  |  | 3084125.9429 | 15972
[5 empty] | Delta |  |  | 84125.9429
KPMG Prototype Use Case 1 | Program Dir | EAG | Fx-SME | Onshore | USA | KPMG | 578.5714 | 11571.4286 | 20 |  |  | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2
| Sr PM | EAG | AI-SME | Onshore | USA | KPMG | 418.5714 | 26788.5714 | 64 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Tech Consultant | EAG | Agent Delivery | Onshore | USA | KPMG | 357.1429 | 114285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Offshore Tech Consultant | EAG | Agent Delivery | Offshore | India | KPMG | 107.1429 | 34285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Offshore Tech Consultant | EAG | Agent Delivery | Offshore | India | KPMG | 107.1429 | 34285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Use Case 1 Support | [7 empty] | 221217.1429 | 1044
KPMG Prototype Use Case 2 | Security Architect | EAG | Fx-SME | Onshore | USA | KPMG | 578.5714 | 11571.4286 | 20 |  |  | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2
| Security Architect | EAG | AI-SME | Onshore | USA | KPMG | 418.5714 | 26788.5714 | 64 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Security Consultant | EAG | Agent Delivery | Onshore | USA | KPMG | 357.1429 | 114285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Security Consultant | EAG | Agent Delivery | Onshore | India | KPMG | 107.1429 | 34285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Security Consultant | EAG | Agent Delivery | Onshore | India | KPMG | 107.1429 | 34285.7143 | 320 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Use Case 2 Support | [7 empty] | 221217.1429 | 1044
[5 empty] | KPMG Total |  |  | 442434.2857 | 2088
Note on P40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Raj Goel - for the 2 agents and a limited group of 40 pilot users, hours can be reduced or are we establishing a champions network and building the strategy and plan they can use for future agents? Reply: Yes ACM team is activating champions network, that will be utilized for future agent adoption tasks, and an adoption strategy for agent adoption in addition to adoption of in-scope agents.

## PRE SRM (Orig)
Area | Role | Area | Project Role | Location | Country | Partner | Bill Rate | Bill Total | Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
[10 empty] | Mobilize & Initiate |  | 3: Solution Modeling, Build, Test, & Deploy
[10 empty] | 2 Weeks |  | 3: 12 Weeks |  | 12 Weeks
Functional Support | Senior Consultant | AIBS | Functional Lead / Delivery Architect | Onshore | USA | Microsoft | 365 | 379600 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Senior Consultant | AIBS | Functional Consultant (Co-Pilot) - Sales / Service / Finance / Ops etc. | Onshore | USA | Microsoft | 365 | 379600 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Functional Support | [7 empty] | 759200 | 2080
Architecture Support | Domain Solution Architect | AIBS | Solution Architect - AIBS | Onshore | USA | Microsoft | 405 | 168480 | 416 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
| Domain Solution Architect | IGD | Solution Architect - IGD | Offshore | India | Microsoft | 90 | 93600 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Domain Solution Architect | AIBS | Solution Architect - TQA | Onshore | USA | Microsoft | 405 | 38880 | 96 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Senior Consultant | AIBS | Integration Architect | Onshore | USA | Microsoft | 365 | 46720 | 128 | 16 | 16 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Architecture Support | [7 empty] | 347680 | 1680
Development Support | Consultant | IGD | Lead Developer ( 100% Lead) | Offshore | India | Microsoft | 90 | 93600 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Copilot / Foundry Developer | Offshore | India | Microsoft | 90 | 93600 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Copilot / Foundry Developer | Offshore | India | Microsoft | 90 | 86400 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Power Automate Developer | Offshore | India | Microsoft | 90 | 86400 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Modern Apps Developer (HITL) | Offshore | India | Microsoft | 90 | 86400 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Consultant | IGD | Data Engineer (Ingestion- Integration) | Offshore | India | Microsoft | 90 | 86400 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Domain Solution Architect | IGD | TQA | Offshore | India | Microsoft | 90 | 17280 | 192 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Consultant | IGD | Test Lead / Tester | Offshore | India | Microsoft | 90 | 86400 | 960 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Development Support | [7 empty] | 636480 | 7072
Infrastructure Support | Consultant | IGD | Infrastructure/Environment Support | Offshore | India | Microsoft | 90 | 28080 | 312 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| Consultant | IGD | Release Manager - Devops / LLMOps | Offshore | India | Microsoft | 90 | 25920 | 288 |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
[8 empty] | 54000 | 600
Project Delivery Support | Delivery Mgmt. Executive | AIBS | Delivery Management | Onshore | USA | Microsoft | 460 | 47840 | 104 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Senior Project Manager | AIBS | Onsite Project Manager | Onshore | USA | Microsoft | 370 | 384800 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Project Manager | IGD | Offshore Project Manager | Offshore | India | Microsoft | 90 | 93600 | 1040 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Delivery Support | [7 empty] | 526240 | 2184
Delivery Compliance, Privacy and Security | Consultant | IGD | Infosec Consultant | Onshore | India | Microsoft | 90 | 9000 | 100 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Security Architect | EAG | Security Architect | Onshore | USA | Microsoft | 445 | 51620 | 116 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Delivery Support | [7 empty] | 60620 | 216
Adoption, Change and Services Management | Sr. Domain Solution Architect | ACM | ACSM Architect | Onshore | USA | Microsoft | 490 | 103880 | 212 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Senior Consultant | ACM | ACM Sr Con (Agent Adoption) | Onshore | USA | Microsoft | 365 | 204400 | 560 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Consultant | ACM | ACM Con (Demos) | Onshore | USA | Microsoft | 300 | 144000 | 480 |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Delivery Support | [7 empty] | 452280 | 1252
Security | Security Architect | EAG | AI Security Foundations | Onshore | USA | Microsoft | 460.58 | 119750.8 | 260 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Security Architect | EAG | Agentic SOC | Onshore | USA | Microsoft | 460.58 | 165808.8 | 360 |  |  | 9: 20; 10: 20; 11: 20; 12: 20; 13: 20; 14: 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Security Consultant | EAG | AI Security Foundations | Onshore | USA | Microsoft | 414 | 198720 | 480 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Security Consultant | EAG | Agentic SOC | Onshore | USA | Microsoft | 414 | 298080 | 720 |  |  | 9: 40; 10: 40; 11: 40; 12: 40; 13: 40; 14: 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Security Consultant | EAG | Agentic SOC | Onshore | USA | Microsoft | 414 | 215280 | 520 |  |  | 9: 40; 10: 40; 11: 40; 12: 40; 13: 40; 14: 40 |  | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Delivery Support | [7 empty] | 997639.6 | 2340
[5 empty] | TOTAL |  |  | 3834139.6 | 17424